## Basic single-project Gantt char
Company name:
Project manager:
Project:
Task | Task owner | Progress | Start date | End date | Start day* | Duration*
Task 1 | Ethan | 100% | 2024-03-04 | 2024-03-08 | 0 | 4
Task 2 | Anna | 100% | 2024-03-08 | 2024-03-13 | 4 | 5
Task 3 | Harriet | 80% | 2024-03-13 | 2024-03-18 | 9 | 5
Task 4 | Sonya | 80% | 2024-03-18 | 2024-03-21 | 14 | 3
Task 5 | David | 80% | 2024-03-21 | 2024-03-25 | 17 | 4
Milestone 1 |  |  | 2024-03-25 | 2024-03-26 | 21 | 1
Task 6 | Ethan | 60% | 2024-03-26 | 2024-04-08 | 22 | 13
Task 7 | Anna | 60% | 2024-04-08 | 2024-04-12 | 35 | 4
Task 8 | Harriet | 60% | 2024-04-12 | 2024-04-17 | 39 | 5
Task 9 | Sonya | 40% | 2024-04-17 | 2024-04-22 | 44 | 5
Task 10 | David | 40% | 2024-04-22 | 2024-04-25 | 49 | 3
Milestone 2 |  |  | 2024-04-25 | 2024-04-26 | 52 | 1
Task 11 | Ethan | 20% | 2024-04-26 | 2024-05-02 | 53 | 6
Task 12 | Anna | 20% | 2024-05-02 | 2024-05-09 | 59 | 7
Task 13 | Harriet | 0% | 2024-05-09 | 2024-05-16 | 66 | 7
Task 14 | Sonya | 0% | 2024-05-16 | 2024-05-20 | 73 | 4
Task 15 | David | 0% | 2024-05-20 | 2024-05-23 | 77 | 3
Milestone 3 |  |  | 2024-05-23 | 2024-05-24 | 80 | 1
* Cells are calculated automatically. | [6 empty] | Monitor your project's progress with Plaky.com

## Advanced single-project Gantt c
Company name:
Project manager:
Project:
Task | Task owner | Progress | Start date | End date | Duration* | Day of the month* | Completed days* | Remaining days*
Task 1 | Ethan | 100% | 2024-03-04 | 2024-03-08 | 4 | 4 | 4 | 0
Task 2 | Anna | 100% | 2024-03-04 | 2024-03-11 | 7 | 4 | 7 | 0
Task 3 | Harriet | 80% | 2024-03-05 | 2024-03-11 | 6 | 5 | 4.8 | 1.2
Task 4 | Sonya | 80% | 2024-03-04 | 2024-03-12 | 8 | 4 | 6.4 | 1.6
Task 5 | David | 60% | 2024-03-05 | 2024-03-13 | 8 | 5 | 4.8 | 3.2
Milestone 1 |  |  | 2024-03-13 | 2024-03-14 | 1 | 13 | 0 | 1
Task 6 | Ethan | 40% | 2024-03-14 | 2024-03-18 | 4 | 14 | 1.6 | 2.4
Task 7 | Anna | 40% | 2024-03-14 | 2024-03-19 | 5 | 14 | 2 | 3
Task 8 | Harriet | 20% | 2024-03-18 | 2024-03-20 | 2 | 18 | 0.4 | 1.6
Task 9 | Sonya | 20% | 2024-03-18 | 2024-03-22 | 4 | 18 | 0.8 | 3.2
Task 10 | David | 0% | 2024-03-20 | 2024-03-25 | 5 | 20 | 0 | 5
Milestone 2 |  |  | 2024-03-25 | 2024-03-26 | 1 | 25 | 0 | 1
Task 11 | Ethan | 0% | 2024-03-26 | 2024-03-28 | 2 | 26 | 0 | 2
Milestone 3 |  |  | 2024-03-28 | 2024-03-29 | 1 | 28 | 0 | 1
* Cells are calculated automatically. | [8 empty] | Monitor your project's progress with Plaky.com

## Basic multi-project Gantt chart
Company name:
Project manager:
| Task | Task owner | Progress | Start date | End date | Start day* | Duration*
Project 1
| Task 1 | Ethan | 100% | 2024-03-04 | 2024-03-08 | 0 | 4
| Task 2 | Anna | 100% | 2024-03-08 | 2024-03-13 | 4 | 5
| Task 3 | Harriet | 80% | 2024-03-13 | 2024-03-18 | 9 | 5
| Task 4 | Sonya | 80% | 2024-03-18 | 2024-03-21 | 14 | 3
| Task 5 | David | 80% | 2024-03-21 | 2024-03-25 | 17 | 4
Project 2
| Task 1 | Ethan | 60% | 2024-03-26 | 2024-04-08 | 0 | 13
| Task 2 | Anna | 60% | 2024-04-08 | 2024-04-12 | 13 | 4
| Task 3 | Harriet | 60% | 2024-04-12 | 2024-04-17 | 17 | 5
| Task 4 | Sonya | 40% | 2024-04-17 | 2024-04-22 | 22 | 5
| Task 5 | David | 40% | 2024-04-22 | 2024-04-25 | 27 | 3
Project 3
| Task 1 | Ethan | 20% | 2024-04-26 | 2024-05-02 | 0 | 6
| Task 2 | Anna | 20% | 2024-05-02 | 2024-05-09 | 6 | 7
| Task 3 | Harriet | 0% | 2024-05-09 | 2024-05-16 | 13 | 7
| Task 4 | Sonya | 0% | 2024-05-16 | 2024-05-20 | 20 | 4
| Task 5 | David | 0% | 2024-05-20 | 2024-05-23 | 24 | 3
* Cells are calculated automatically. | [7 empty] | Monitor your project's progress with Plaky.com

## Advanced multi-project Gantt ch
Company name:
Project manager:
| Task | Task owner | Progress | Start date | End date | Duration* | Day of the month* | Completed days* | Remaining days*
Project 1
| Task 1 | Ethan | 100% | 2024-03-04 | 2024-03-08 | 4 | 4 | 4 | 0
| Task 2 | Anna | 100% | 2024-03-04 | 2024-03-08 | 4 | 4 | 4 | 0
| Task 3 | Harriet | 80% | 2024-03-05 | 2024-03-11 | 6 | 5 | 4.8 | 1.2
| Task 4 | Sonya | 80% | 2024-03-05 | 2024-03-12 | 7 | 5 | 5.6 | 1.4
| Task 5 | David | 80% | 2024-03-06 | 2024-03-12 | 6 | 6 | 4.8 | 1.2
Project 2
| Task 1 | Ethan | 60% | 2024-03-13 | 2024-03-18 | 5 | 13 | 3 | 2
| Task 2 | Anna | 60% | 2024-03-13 | 2024-03-18 | 5 | 13 | 3 | 2
| Task 3 | Harriet | 60% | 2024-03-14 | 2024-03-18 | 4 | 14 | 2.4 | 1.6
| Task 4 | Sonya | 40% | 2024-03-19 | 2024-03-22 | 3 | 19 | 1.2 | 1.8
| Task 5 | David | 40% | 2024-03-19 | 2024-03-25 | 6 | 19 | 2.4 | 3.6
Project 3
| Task 1 | Ethan | 20% | 2024-03-26 | 2024-03-28 | 2 | 26 | 0.4 | 1.6
| Task 2 | Anna | 20% | 2024-03-26 | 2024-03-28 | 2 | 26 | 0.4 | 1.6
| Task 3 | Harriet | 0% | 2024-03-26 | 2024-03-29 | 3 | 26 | 0 | 3
| Task 4 | Sonya | 0% | 2024-03-27 | 2024-03-29 | 2 | 27 | 0 | 2
| Task 5 | David | 0% | 2024-03-28 | 2024-03-29 | 1 | 28 | 0 | 1
* Cells are calculated automatically. | [9 empty] | Monitor your project's progress with Plaky.com

## Manual Gantt chart
Company name:
Project manager:
Project:
Task | Task owner | Progress | Start date | End date | Duration* | 2024-03-01
[6 empty] | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31
Task 1 | Ethan | 100% | 2024-03-01 | 2024-03-04 | 4
Task 2 | Anna | 80% | 2024-03-04 | 2024-03-06 | 3
Task 3 | Harriet | 60% | 2024-03-06 | 2024-03-08 | 3
Task 4 | Sonya | 40% | 2024-03-08 | 2024-03-12 | 5
Task 5 | David | 20% | 2024-03-12 | 2024-03-14 | 3
Task 6 | Ethan | 0% | 2024-03-14 | 2024-03-19 | 6
Task 7 | Anna | 100% | 2024-03-19 | 2024-03-21 | 3
Task 8 | Harriet | 80% | 2024-03-21 | 2024-03-25 | 5
Task 9 | Sonya | 60% | 2024-03-25 | 2024-03-27 | 3
Task 10 | David | 40% | 2024-03-27 | 2024-03-28 | 2
* Cells are calculated automatically. | [5 empty] | 2024-03-01: Monitor your project's progress with Plaky.com