## Project
|  | Gantt Chart Template | [6 empty] | Project manager: |  | Andrew S. | Project start: | 2024-02-26
[17 empty] | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05
# | Type | Project items | Description | Team | Assignee | ! | Start date (manual input) | Due date (manual input) | No. of workdays | Start date | Due date | % | Status | Estim. budget | Actual budget | Difference | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | P | Phase1 |  | Marketing | Sabrina B. |  | 2024-03-11 | 2024-03-22 | 15 | 2024-03-11 | 2024-03-29 | 20% |  | 1000 | 340 | 660
2 | T | Task1 |  | Dev | Jenny A. |  | 2024-03-12 |  | 3 | 2024-03-12 | 2024-03-14 | 10% | In Progress | 200 | 110 | 90
3 | T | Task2 |  | Security | Tom D. | ! | 2024-03-13 |  | 3 | 2024-03-13 | 2024-03-15 | 100% | Completed | 200 | 230 | -30
4 | T | Task3 |  | Sales | Gabriel G. |  | 2024-03-14 |  | 4 | 2024-03-14 | 2024-03-19 | 50% | In Progress
5 | T | Task4 |  | PM | Jose E. |  |  | 2024-03-29 | 6 | 2024-03-22 | 2024-03-29
6 | T | Task5 |  | PM | Jose E. | ! | 2024-03-19 |  | 7 | 2024-03-19 | 2024-03-27 | 100% | In Review
7 | M | Milestone1 |  | PM | Jose E. |  | 2024-03-20 |  |  | 2024-03-20 | 2024-03-20 |  | On Hold | bar: 2024-03-20
8 | P | Phase2
9 | T | Task1
10 | T | Task2
11 | T | Task3
12 | T | Task4
13 | M | Milestone2
14
15
16
17
18
19
20
21
22
23
24
25
Settings
Manage your project with Plaky
Help

## Settings
Settings
Project details |  | Holidays | Scroll Bar | Project role types |  |  | Project team |  |  | Status dropdown
Project title |  | 2024-12-25 | 0 | Role | Code | # | Name | Role | Code | In Progress
Project manager | Andrew S. | 2024-07-04 |  | Development | Dev | 1 | Jenny A. | Development | Dev | In Review
Project start date | 2024-02-26 |  |  | Marketing | Marketing | 1 | Sabrina B. | Marketing | Marketing | Completed
Project end date |  |  |  | Security | Security | 1 | Peter C. | Design | Design | Blocked
|  |  |  | Design | Design | 1 | Tom D. | Security | Security | On Hold
|  |  |  | Content | Content | 0 | Jose E. | Project management | PM
|  |  |  | Project management | PM | 1 | Mary F. | HR | HR
|  |  |  | HR | HR | 1 | Gabriel G. | Sales | Sales
|  |  |  | QA | QA | 0
|  |  |  | Finance | Finance | 0
|  |  |  | Support | Support | 0
|  |  |  | Sales | Sales | 1
|  |  |  | Administration | Admin. | 0
Today's date: | 45376 |  |  | SEO | SEO | 0
|  |  |  | PR | PR | 0
Manage your project with Plaky
Help
Project

## Help
Help: How to use and customize this template
Manage your project with Plaky
Settings
Project
Title bar:
To set your project title, project manager, and project start dates, you may type in the information directly in the title bar, or (recommended) go to the “Settings” tab at the bottom left of the screen or click on the “Settings” button in the title bar. and fill out the “Project details” table. The information from the “Project details” table will reflect in your main title bar and it will ensure that you don’t accidentally change or delete the info while working on the main sheet.
Main table:
To start using the Gantt chart and project table, write the names of your project phases, tasks and milestones in the “Project items” column. In the “Type” column, select the letters “P”, “T”, or “M” to mark whether the item next to it is a phase, task, or milestone. This column mainly exists for formatting purposes — once you select the type you want, the table formatting will adjust accordingly. If you delete the “Type” column, the formatting will disappear.
Description:
Use the “Description” column to add more information about the project items.
Assignee:
The “Assignee” column is for adding the people responsible for the project item in question. To add an assignee, simply select their name from the dropdown list.
If the person you’re looking for is not in the dropdown list, go to the “Settings” tab in the bottom left corner of the screen or click on the “Settings” button in the title bar and add their name and role to the “Project team” table.
Once you do this, their name will appear in the dropdown list.
If you decide to remove someone from the team, simply delete their name from the “Project team” table in the “Settings” tab. In the case that their name still exists in the “Assignee” column of the main table, their name will appear red. This will let you know that that item should be reassigned to another team member.
Team:
There is no need to add anything to the “Team” column in the main table—the table will populate automatically once you select the assignee. If the “Team” column doesn’t automatically populate, read further instructions under the “Customization” subheading below.
! Column
The “!” column is meant for marking tasks/projects/milestones that are in danger (it’s up to you to decide what this means for your project). It’s also up to you whether you want to use it or not. To mark that an item is in danger, choose the “!” from the dropdown list. To delete the “!”, simply click on the cell and press “delete” on mac or “backspace” on Windows. You may also completely delete this column without affecting any existing formulae in the table.
2 types of start date and due date columns:
You might be confused as to why there are 2 types of start date and due date columns.
The “Start date (manual input)” and “Due date (manual input)” columns are where you can manually write the start and end dates for your phases/tasks/milestones. Whatever you write in these columns will be reflected and automatically calculated in the “Start date’ and “Due date” columns marked in light blue, based on the number of work days the task is expected to take.
The start and end dates of your phases/tasks will be automatically reflected in the Gantt chart.
Only one of the “manual” date columns can be active at a time. You can only have 1 of the 2 columns filled out. If you have both of them filled out, the date that’s currently inactive will be grayed out for your convenience.
Example: if you write “4-Mar-24” in the “Start date (manual input)” column, and designate 7 workdays to that task, the automatic “Start date” column will show “4-Mar-24” as the start date and “12-Mar-24” as the automatic “Due date” (because the formula skips weekends and any designated holidays from the calculation).
On the other hand, if you know when your due date is and how many days you need to complete the task, the formula will calculate when you need to start the task so that you can finish it on time.
What you need to do in this case is write the expected due date in the “Due date (manual input)” column and the expected number of work days it will take to finish the task. The formula will then calculate the start date backwards and show it in the automatic “Start date” column.
No. of work days:
Use the “No. of work days” to write how many days a task is expected to take. This column is important for calculating the automatic start and due dates for a task. Without it, the Gantt chart won’t work as intended.
The number of work days designated to tasks should be input manually. But, the number of work days for a phase will be calculated automatically based on the earliest start date and the latest end date of the tasks.
% Column
The “%” column is for visual reference of how the phase/task is progressing and it should be updated manually.
Status column
The “Status” column shows the current status of the task/phase/milestone. To set the status, simply choose an option from the drop down list. If the option you’re looking for is not available or you wish to modify an existing option, go to the “Settings” tab in the bottom left corner of the screen or click on the “Settings” button in the title bar and find the “Status dropdown” table. Here you can add a new option or edit an existing one, as long as it’s within the boundaries of the table (the gray fields).
Budget columns
The “Estim. budget” and “Actual budget” columns are manual input columns, while the “Difference” is automatically calculated by subtracting the actual budget from the estimated budget.
If the difference is less than 0, the number will show up red to indicate that the budget for that particular task has been overrun.
Gantt chart
The Gantt chart will automatically reflect all changes made to the start and end dates for each phase/task/milestone.
The phases will be shown in dark gray, while the tasks belonging to those phases will show up in light gray. The milestone dates are marked with a gray dot.
All weekends and designated holidays are excluded from the Gantt chart, and the weeks are separated by a vertical gray line.
Excel will recognize what day it is and will reflect that in the Gantt chart. The date will automatically update every day (no need for you to do anything). Today’s date will be marked in blue in the Gantt chart and it will also show up as a dark vertical line spanning the entire chart.
The current Gantt chart shows a span of 100 days, while only 30 are immediately visible. To show more days, move the scroll bar above the Gantt chart.
The current Gantt chart is able to show up to 100 days. If you want to change the number of days shown in the Gantt chart, right click on the scroll bar, select “Format Control” and change the “Maximum value” to any number you want.
E.g., if your project is expected to last 1 year, you can increase the maximum value to around 400. This will account for 365 days + some wiggle room. This number can always be changed.
Customization
Most of the customization options are available in the “Settings” tab (click on the “Settings” button in the title bar).
The “Project details” table shows the basic project information. The project title, manager, and start date will be reflected in the title bar of the main tab where the Gantt chart is.
The “Holidays” table shows a list of holidays that are non-working days. The holidays you designate here will reflect in the start date and due date calculations and will not show up in the Gantt chart. You may add as many holidays as there are gray rows in the column.
The “Project role types” lists all the roles that exist in your project, and the “Code” column shows how you want those roles to appear in the main table. You may use full role names or abbreviations as you see fit.
Feel free to delete or change the roles that currently exist in the table or add new ones (as long as it’s within the bounds of the table, i.e., the gray cells). In case you need more rows, feel free to insert additional rows anywhere between rows 5 and 23 (it will not break the formula).
The formula will not work only if you add more roles in cells that are not colored gray, i.e., under the table.
The “#” column counts how many people have that particular role assigned to them in the “Project team” table to the right.
The “Project team” table shows the names of all your team members and their designated role. Once you add a team member and their role to this table, their name will appear in the dropdown list in the main table, and their “Team” column will automatically populate.
If the “Team” column doesn’t automatically populate once you add an assignee, it likely means that you haven’t added their unique role to the “Project role types” table.
The “Project role types” and the “Project team” tables are connected and the “Project team” table pulls information from the “Project role types” table. So, while it’s not important in which order you add information, it might be best to first add all your project roles and then assign people to those roles, so that there’s no confusion later.
If you delete a person from your project team, their name will show up red in the main table to indicate that that particular task needs to be reassigned.
Please do NOT write or change anything in the tables outlined in red.
There are minimization buttons at the top of the page—you can collapse the manual date columns and the budget columns to get a better overview of the table and Gantt chart without having to scroll left and right.
NOTE: if you change any of the names in the “Status dropdown” list, or add any new options, those options will not be colored. To color these new options, select the column and go to:
“Home” tab at the top > Conditional Formatting > New Rule > Format only cells that contain
In the “Cell value” choose “Specific text“ and then write the exact name of the new option.
Once you do this, you can click on the “Format” button below and choose how you want it to be colored, outlined, etc., and save the changes by clicking “Ok”.
To modify Existing Conditional Formatting options, go to:
Home > Conditional Formatting > Manage Rules

## Disclaimer
Disclaimer
Manage your project with Plaky
This template is for reference only.
Plaky aims to provide the most accurate and up-to-date information at all times. Plaky makes no warranties or representations of any kind, expressed or implied, about the accuracy, completeness, and reliability of the information and formulas provided in this template. Plaky shall not be liable for any indirect, incidental, special, consequential, or exemplary damages, or any loss of profits or revenues caused directly or indirectly by the use of this template. Plaky shall not be liable for any loss of data, goodwill, use, or any other intangible losses arising out of your access to, use, or inability to use this template. Use this template at your own risk.
Settings
Help
Project