## Dashboard
Project Management Dashboard Template |  |  |  |  | Jan 3, 2024 — Oct 16, 2024
Start date: | 2024-01-01 |  | Project manager: |  | Peter Maxwell | [8 empty] | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16
Project | Tasks | Priority | Department | Assignee | Manager | Status | Start date | Duration | Due date | Days left | Progress | Budget | Actual cost | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
ALPHA | Task1 | Low | Development | Jasmine C. | Kevin J. | In Review | 2024-01-11 | 3 | 2024-01-15 | -41 | 100% | 1000 | 999
| Task2 | Medium | Marketing | Tom D. | Prudence P. | In Progress | 2024-01-06 | 50 | 2024-03-15 | 5 | 95% | 1000 | 1000
| Task5 | Medium | Design | George H. | Jason B. | On Hold | 2024-02-02 | 10 | 2024-02-15 | -18 | 15% | 23000 | 12000
| Task23 | High | Security | Alexander G. | Sasha H. | Not started | 2024-04-16 | (blank) |  | - |  | 2000 | 0
| Task24 | Medium | Design | George H. | Jason B. | In Progress | 2024-01-03 | 176 | 2024-09-05 | 128 | 70% | 22000 | 18600
BETA | Task3 | Critical! | Marketing | Jenna A. | Prudence P. | On Hold | 2024-02-27 | 30 | 2024-04-08 | 21 | 30% | 1000 | 1001
| Task6 | High | Content | David E. | Helen C. | Complete | 2024-02-20 | 65 | 2024-05-20 | - | 100% | 43000 | 40000
| Task7 | Medium | Development | Davina B. | Kevin J. | Overdue | 2024-01-28 | 20 | 2024-02-23 | -12 | 50% | 6000 | 6600
| Task14 | Medium | Security | Alexander G. | Sasha H. | Complete | 2024-01-03 | 43 | 2024-03-01 | - | 100% | 34000 | 33700
| Task15 | Medium | Marketing | Tom D. | Prudence P. | In Review | 2024-01-06 | 185 | 2024-09-23 | 140 | 100% | 11500 | 11100
| Task26 | Medium | Development | Peter I. | Kevin J. | Complete | 2024-01-28 | 130 | 2024-07-29 | - | 100% | 14500 | 15700
DELTA | Task11 | Critical! | Content | David E. | Helen C. | Complete | 2024-01-11 | 50 | 2024-03-20 | - | 100% | 1800 | 1500
| Task12 | High | Content | David E. | Helen C. | In Progress | 2024-02-12 | 300 | 2025-04-08 | 280 | 30% | 19000 | 21300
| Task16 | Medium | Development | Tom D. | Kevin J. | In Progress | 2024-01-28 | 320 | 2025-04-22 | 290 | 10% | 3800 | 800
| Task17 | Medium | Development | Davina B. | Kevin J. | In Progress | 2024-01-07 | 220 | 2024-11-11 | 175 | 25% | 4900 | 2000
| Task18 | Critical! | Content | David E. | Helen C. | On Hold | 2024-01-08 | 173 | 2024-09-05 | 128 | 80% | 5000 | 600
| Task25 | Low | Content | David E. | Helen C. | On Hold | 2024-02-06 | 100 | 2024-06-24 | 76 |  | 13600 | 0
| Task27 | Critical! | Development | Jenna A. | Kevin J. | Blocked | 2024-02-27 | (blank) |  | - | 30% | 20000 | 4000
GAMMA | Task8 | Low | Development | Davina B. | Kevin J. | In Progress | 2024-01-11 | 65 | 2024-04-10 | 23 | 30% | 16000 | 16200
| Task13 | Low | Security | Samantha F. | Sasha H. | On Hold | 2024-10-16 | (blank) |  | - |  | 9000 | 0
| Task20 | High | Security | Alexander G. | Sasha H. | In Review | 2024-01-18 | 200 | 2024-10-24 | 163 | 100% | 43000 | 36000
| Task28 | Low | Marketing | Tom D. | Prudence P. | Complete | 2024-01-14 | 70 | 2024-04-19 | - | 100% | 10000 | 12000
OMEGA | Task4 | High | Security | Samantha F. | Sasha H. | Overdue | 2024-02-14 | 10 | 2024-02-27 | -10 | 5% | 5000 | 4500
| Task9 | Low | Design | George H. | Jason B. | Overdue | 2024-01-05 | 11 | 2024-01-19 | -37 | 70% | 2000 | 2000
| Task10 | Medium | Development | Jasmine C. | Kevin J. | Complete | 2024-01-10 | 30 | 2024-02-20 | - | 100% | 22000 | 23500
| Task19 | Medium | Marketing | Tom D. | Prudence P. | Overdue | 2024-01-23 | 25 | 2024-02-26 | -11 | 5% | 23000 | 20000
| Task21 | Low | Marketing | Jenna A. | Prudence P. | Overdue | 2024-01-21 | 20 | 2024-02-16 | -17 | 50% | 6000 | 9000
| Task22 | Low | Design | George H. | Jason B. | Complete | 2024-01-12 | 260 | 2025-01-13 | - | 100% | 16000 | 16300
Grand Total | [10 empty] | 63.8% | 379100 | 310400
82%
Go to Project
Manage your project in Plaky
25%
Settings
Help
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Table
Project Management Template With Dashboard
Project manager |  | Peter Maxwell | Client |  | Project summary
Project start date |  | 2024-01-01 | Sponsor |  | The goal of this project is to…
Project end date |  |  | Total budget
Project | ! | Tasks | Priority | Description | Department | Assignee | Manager | Status | Progress | Start date | Duration | Due date | Days left | Budget | Actual cost | Notes
ALPHA | r | Task1 | Low |  | Development | Jasmine C. | Kevin J. | In Review | 100% | 2024-01-11 | 3 | 2024-01-15 | -51 | 1000 | 999
ALPHA | r | Task2 | Medium |  | Marketing | Tom D. | Prudence P. | In Progress | 95% | 2024-01-06 | 50 | 2024-03-15 | -7 | 1000 | 1000
BETA |  | Task3 | Critical! |  | Marketing | Jenna A. | Prudence P. | On Hold | 30% | 2024-02-27 | 30 | 2024-04-08 | 11 | 1000 | 1001
OMEGA | r | Task4 | High |  | Security | Samantha F. | Sasha H. | Overdue | 5% | 2024-02-14 | 10 | 2024-02-27 | -20 | 5000 | 4500
ALPHA | r | Task5 | Medium |  | Design | George H. | Jason B. | On Hold | 15% | 2024-02-02 | 10 | 2024-02-15 | -28 | 23000 | 12000
BETA | a | Task6 | High |  | Content | David E. | Helen C. | Complete | 100% | 2024-02-20 | 65 | 2024-05-20 | - | 43000 | 40000
BETA | r | Task7 | Medium |  | Development | Davina B. | Kevin J. | Overdue | 50% | 2024-01-28 | 20 | 2024-02-23 | -22 | 6000 | 6600
GAMMA |  | Task8 | Low |  | Development | Davina B. | Kevin J. | In Progress | 30% | 2024-01-11 | 65 | 2024-04-10 | 13 | 16000 | 16200
OMEGA | r | Task9 | Low |  | Design | George H. | Jason B. | Overdue | 70% | 2024-01-05 | 11 | 2024-01-19 | -47 | 2000 | 2000
OMEGA | a | Task10 | Medium |  | Development | Jasmine C. | Kevin J. | Complete | 100% | 2024-01-10 | 30 | 2024-02-20 | - | 22000 | 23500
DELTA | a | Task11 | Critical! |  | Content | David E. | Helen C. | Complete | 100% | 2024-01-11 | 50 | 2024-03-20 | - | 1800 | 1500
DELTA |  | Task12 | High |  | Content | David E. | Helen C. | In Progress | 30% | 2024-02-12 | 300 | 2025-04-08 | 270 | 19000 | 21300
GAMMA |  | Task13 | Low |  | Security | Samantha F. | Sasha H. | On Hold |  | 2024-10-16 |  |  | - | 9000 | 0
BETA | a | Task14 | Medium |  | Security | Alexander G. | Sasha H. | Complete | 100% | 2024-01-03 | 43 | 2024-03-01 | - | 34000 | 33700
BETA |  | Task15 | Medium |  | Marketing | Tom D. | Prudence P. | In Review | 100% | 2024-01-06 | 185 | 2024-09-23 | 130 | 11500 | 11100
DELTA |  | Task16 | Medium |  | Development | Tom D. | Kevin J. | In Progress | 10% | 2024-01-28 | 320 | 2025-04-22 | 280 | 3800 | 800
DELTA |  | Task17 | Medium |  | Development | Davina B. | Kevin J. | In Progress | 25% | 2024-01-07 | 220 | 2024-11-11 | 165 | 4900 | 2000
DELTA |  | Task18 | Critical! |  | Content | David E. | Helen C. | On Hold | 80% | 2024-01-08 | 173 | 2024-09-05 | 118 | 5000 | 600
OMEGA | r | Task19 | Medium |  | Marketing | Tom D. | Prudence P. | Overdue | 5% | 2024-01-23 | 25 | 2024-02-26 | -21 | 23000 | 20000
GAMMA |  | Task20 | High |  | Security | Alexander G. | Sasha H. | In Review | 100% | 2024-01-18 | 200 | 2024-10-24 | 153 | 43000 | 36000
OMEGA | r | Task21 | Low |  | Marketing | Jenna A. | Prudence P. | Overdue | 50% | 2024-01-21 | 20 | 2024-02-16 | -27 | 6000 | 9000
OMEGA | a | Task22 | Low |  | Design | George H. | Jason B. | Complete | 100% | 2024-01-12 | 260 | 2025-01-13 | - | 16000 | 16300
ALPHA |  | Task23 | High |  | Security | Alexander G. | Sasha H. | Not started |  | 2024-04-16 |  |  | - | 2000 | 0
ALPHA |  | Task24 | Medium |  | Design | George H. | Jason B. | In Progress | 70% | 2024-01-03 | 176 | 2024-09-05 | 118 | 22000 | 18600
DELTA |  | Task25 | Low |  | Content | David E. | Helen C. | On Hold |  | 2024-02-06 | 100 | 2024-06-24 | 66 | 13600 | 0
BETA | a | Task26 | Medium |  | Development | Peter I. | Kevin J. | Complete | 100% | 2024-01-28 | 130 | 2024-07-29 | - | 14500 | 15700
DELTA |  | Task27 | Critical! |  | Development | Jenna A. | Kevin J. | Blocked | 30% | 2024-02-27 |  |  | - | 20000 | 4000
GAMMA | a | Task28 | Low |  | Marketing | Tom D. | Prudence P. | Complete | 100% | 2024-01-14 | 70 | 2024-04-19 | - | 10000 | 12000
Formulas:
Due date = IF(AND(ProjectTable[[#This Row],[Start date]]<>"",[Duration]<>""),WORKDAY.INTL(ProjectTable[[#This Row],[Start date]]-1,[Duration],1,Settings!$G4:G52),"")
Days left = IF(OR('Project Table'!$[Status]="Complete",ProjectTable[[#This Row],[Due date]]=""),"-",NETWORKDAYS.INTL(TODAY(),'Project Table'!$[Due date],1,Settings!$G4:G42))
Dashboard
Manage your project with Plaky
Settings
Help
Note on E6: To change the values in the dropdown list, go to the next sheet and simply replace a value with a custom one in the "Priority dropdown" column. Example: You wish to replace the value "Medium" in the dropdown list to "Unknown". Step1: Click on "Sheet2" at the bottom left of the screen. Step2: In the "Priority dropdown" column, locate the cell that says "Medium". Step3: Delete "Medium" and replace it with "Unknown" (or any other value of your choosing). You can use the same method to replace the values in the dropdown list of the "Status" column.
Note on K6: You can choose the percentage via the dropdown list, or you can type in a custom number. Note: The bar will not automatically change to "100%" if the status is changed to "Complete".

## Settings
Settings
[5 empty] | Holidays | Today's date: | 2024-03-25
Priority dropdown | Status dropdown | Department | Assignee | Manager | 2024-12-25 | Show "i" notification | 4 | days before the deadline
High | In Progress | Development | Jenna A. | Kevin J. | 2024-07-04
Medium | Complete | Marketing | Davina B. | Helen C.
Low | In Review | Security | Jasmine C. | Sasha H.
Critical! | On Hold | Design | Tom D. | Prudence P.
| Blocked | Content | David E. | Jason B.
| Overdue | Project management | Samantha F.
| Not started | HR | Alexander G.
|  | QA | George H.
|  | Finance | Peter I.
Support
Sales
Administration
SEO
Product management
Product 1
Product 2
Product 3
PR
Go to Dashboard
Manage your project with Plaky
Go to Project
Help

## Formulae for the dashboard
Status dropdown |  |  | Actual cost | Budget |  |  | % Duration of project |  |  | Remaining % of project
|  | Bar chart | 310400 | 379100 | Scroll bar: | 79 | Project | Tasks | Status | Number of tasks total | 28
In Progress | 6 | Doughnut | 81.88% | 18.12% |  |  | ALPHA | Task1 | In Review | Number of "Complete" tasks | 7 | Today's date: | 45376
Complete | 7 | [6 empty] | Task2 | In Progress | Number of remaining tasks | 21
In Review | 3 | [6 empty] | Task5 | On Hold
On Hold | 5 | [6 empty] | Task23 | Not started | Complete | 25%
Blocked | 1 | [6 empty] | Task24 | In Progress | Remaining | 75%
Overdue | 5 | [5 empty] | BETA | Task3 | On Hold
Not started | 1 | [6 empty] | Task6 | Complete
[8 empty] | Task7 | Overdue
[8 empty] | Task14 | Complete
Remaining tasks | 7 | [6 empty] | Task15 | In Review
Total tasks | 28 | [6 empty] | Task26 | Complete
[7 empty] | DELTA | Task11 | Complete
[8 empty] | Task12 | In Progress
[8 empty] | Task16 | In Progress
[8 empty] | Task17 | In Progress
[8 empty] | Task18 | On Hold
[8 empty] | Task25 | On Hold
[8 empty] | Task27 | Blocked
[7 empty] | GAMMA | Task8 | In Progress
[8 empty] | Task13 | On Hold
[8 empty] | Task20 | In Review
[8 empty] | Task28 | Complete
[7 empty] | OMEGA | Task4 | Overdue
[8 empty] | Task9 | Overdue
[8 empty] | Task10 | Complete
[8 empty] | Task19 | Overdue
[8 empty] | Task21 | Overdue
[8 empty] | Task22 | Complete
Grand Total

## Help
Help: How to use and customize this template
Go to Dashboard
Manage your project with Plaky
Go to Project
Settings
Title bar — Dashboard:
The title bar in the dashboard sheet shows the project title and the duration of the project (the data reflects the earliest start date and the latest end date from the table).
You may change the project title manually. There is no need to change the project start and end dates—these will update automatically as you change the start and end dates in the table, or as you filter the table.
Chart area:
Under the title bar, you’ll find the area showing the main project charts:
- The total completed percentage of the project,
- The status bar reflecting the number of tasks by status (hover over the bar to see what each color represents),
- The total budget spent, and
- The comparison between the planned and actual budget for the entire project.
These charts reflect the information from the table. In case they fail to present the accurate information, go to Data > Refresh
Title area2:
Under the chart area, you’ll find a field showing your project start date and project manager. These fields reflect the same fields from the table on the “Project table” tab.
Unlike the start and end dates of the project at the very top of the template that change as you update the project table or filter the data, this project start date will not change unless you change the start data in the “Project table” tab of the template.
To the right of this field, you’ll also find a “Go to Project” button that will lead you directly to the just mentioned “Project table” tab.
Left sidebar:
The slicers enable you to easily filter through the information in the table. You can have multiple filters applied to your data at any one time.
The table can also be filtered using the arrow buttons at the top of each column. If you’d like to add more slicers to the table, go to:
“Insert” tab at the top of the page > Slicer
And then choose which slicers you’d like to insert from the options you’re offered.
Main table:
The main table is a pivot table that reflects all the same data that exists in your “Project table” where you actually track your project. In case the table doesn’t show correct data, go to Data > Refresh
You can filter the information in the table using the arrow buttons at the top of each column or using slicers. The filtered data will be reflected in the charts above, in the dates at the top of the page and in the Gantt chart.
Gantt chart:
The Gantt chart shows a visual representation of the start and end dates for your project tasks and their progress.
The chart shows 30 days at a time. To see more days, move the scroll bar above the Gantt chart.
The weekends and holidays in the chart are marked with cross-hatching, and today’s date is marked with a blue color and a dark vertical line across the entirety of the chart.
The current Gantt chart is able to show up to 500 days. If you want to change the number of days shown in the Gantt chart, right click on the scroll bar, select “Format Control” and change the “Maximum value” to any number you want.
E.g., if your project is expected to last 2 years, you can increase the maximum value to around 750+. This will account for 365 days x2 with some wiggle room. This number can always be changed.
Title bar — Project table
The title bar in the Project table shows the project title that you can update manually, and the “Go to Dashboard” button that will instantly lead you to the tab with the dashboard.
Project info table:
Under the title chart you’ll find a table for writing down the start and end dates, name of the project manager, client, and sponsor, as well as the total project budget, and a short project summary.
The name of the project manager and the project start date you write in this table will be reflected in the project dashboard, above the main table.
Main table:
This is the main table meant to be used for tracking the actual project.
Project:
In the project field you can write down the name of each of your projects you
re tracking. When you add the name of the project next to a task that belongs to that project, you'll be able to filter your table by project and see only the tasks related to a certain project.
Tasks:
In the tasks column you can break down each of your project into tasks/activities. Be sure to give them a short and recognizable name.
The column next to the “Task” column gives you a quick preview of the tasks that have been completed (will display a checkmark), the tasks that are overdue (will display an X), or tasks whose deadline is 3 days or fewer away (will display a yellow “i” sign). This column is optional and you may delete it if you think it’s unnecessary.
Priority:
The priority column is where you set your subtask’s priority (low, medium, high, or critical) from the dropdown list.
To add or remove priority labels from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Priority dropdown” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 10 to get additional gray rows.
Description:
This is where you add additional information and details about each subtask.
Department:
The department column is where you indicate which team is responsible for a particular task. There are options available in the dropdown list.
To add or remove department options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Department” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 50 to get additional gray rows.
Assignee:
The Assignee column is where you indicate which person is responsible for a particular task. There are options available in the dropdown list.
To add or remove assignee options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Assignee” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 202 to get additional gray rows.
Manager:
The Manager column is where you indicate which person is responsible for the team/assignee for a particular task. There are options available in the dropdown list.
To add or remove manager options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Manager” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 52 to get additional gray rows.
Status:
In the status column, you’ll be able to choose your subtask’s status from a dropdown list. There are currently 7 different types of statuses available in the dropdown list.
To add or remove status options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Status dropdown” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 15 to get additional gray rows.
Progress:
The progress column is a visual representation of each subtask’s progress. It does not pull information from any source and must be updated manually. You can choose an option from the dropdown list, or type in a custom percentage.
NOTE: If you type in a custom percentage that doesn’t exist in the dropdown list, the cell will have a small triangle at the top left corner and might indicate that there is an error in the cell. You may ignore this warning as this is a manually-updated column and doesn’t affect any of the calculations.
Start date + Duration + End date + Days left
The “Start date” column is where you manually write down the date you expect your subtask to start.
The “Duration” column is where you write down the number of work days you expect your subtask to take (the calculation will exclude weekends and any designated holidays). Once you input the expected duration, the “End date” will automatically show up.
To add or remove holidays from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Holidays” column. You may add new holidays as long as there are gray fields left in the column. If you need to add more holidays, you’ll have to insert a new row between rows 2 and 41 to get additional gray rows.
Once you have your end date, the “Days left” column will automatically calculate how many days you have left until the deadline, or if your deadline has passed, how many days you are behind schedule.
Budget:
The “Budget” and “Actual cost” columns are where you can manually input your subtask budget and the actual money funds spent on performing that task. The actual cost that exceeds the budget set out for that task will show up in red.
Important!
Please do NOT change or remove anything in the “Formulae for the dashboard” tab at the bottom left of the screen. If you do, the dashboard might not work properly anymore.

## Disclaimer
Disclaimer
Dashboard
Manage your project with Plaky
Settings
Go to Project
Help
This template is for reference only.
Plaky aims to provide the most accurate and up-to-date information at all times. Plaky makes no warranties or representations of any kind, expressed or implied, about the accuracy, completeness, and reliability of the information and formulas provided in this template. Plaky shall not be liable for any indirect, incidental, special, consequential, or exemplary damages, or any loss of profits or revenues caused directly or indirectly by the use of this template. Plaky shall not be liable for any loss of data, goodwill, use, or any other intangible losses arising out of your access to, use, or inability to use this template. Use this template at your own risk.