## Project Budget
Project Budgeting Template
Project manager: |  | Alyssa S.
Total project budget: |  | 2000000
Estim. project budget: |  | 1800000
Actual total costs: |  | 27580
Total spent
[7 empty] | 27980 |  |  |  | 26330 |  |  |  |  | 4840 |  | 1250 |  | 27580
[7 empty] | Estm. materials/resource expenses |  |  |  | Actual materials/resource expenses |  |  |  |  | Contingency budget (from allocated) |  | Contingency expenses |  | Budget
Project | Task | Category | Subcategory | Type | Inter/Exter | Description | Estm. Quantity | Unit | Estm. price per unit | Estm. cost | Actual quantity | Unit | Actual price per unit | Actual cost | Cost variance | % | Total | Description | Cost | Allocated budget/task | Estm. budget per task | Actual budget per task
Alpha | New drawing tablets | Design | Office | One-time | Internal | Added new members, need new equipment | 3 | pcs | 650 | 1950 | 2 | pcs | 650 | 1300 | 650 | 10% | 300 | 1 new GPU + installation fees (GPU broke) | 1250 | 3000 | 1950 | 2550
Beta | Customs fee | Acquisition | Customs | One-time | External | Customs fee for transport of X parts | 1 | pcs | 30 | 30 | 1 | pcs | 30 | 30 | 0 | 5% | 40 |  |  | 800 | 600 | 30
Beta | Construction workers' wage | Construction | Labor | Recurring | External | Weekly wages for construction workers | 52 | week | 500 | 26000 | 50 | pcs | 500 | 25000 | 1000 | 15% | 4500 |  |  | 30000 | 26000 | 25000
Manage your project with Plaky
Help
Settings

## Settings
Settings
NOTE: | The table below is the basis for all the dropdown lists in the main table. All the data in the table below is purely sample data. You're invited to delete/change/add items as you see fit. E.g., if you want your "Category" dropdown to show different options than it does currently, simply delete everything in the "Category" column below and write your own, custom options. Whatevery you write in these columns will appear in the dropdown lists in the corresponding column in the main table. Once you're ready to start using this template, it's recommended that you delete everything in the table below and start from scratch, so that you can customize the options to fit your specific project(s). Likewise, you may change the column titles in the main table if the current ones don't fit your project, just make sure to not change the purpose of the columns that are included in table formulas (e.g., the "allocated budget for materials" column can have a different name, but it must be used for that exact purpose, otherwise the cost variance calculation and the budget calculations at the end of the table won't make sense). For more in-depth instructions on how to customize this template, go to the Help tab in the bottom left corner or use the button at the top right of the page.
|  |  | Project | Category | Subcategory | Type | Inter/Exter | Unit
|  |  | Alpha | Design | Product | One-time | Internal | pcs
|  |  | Beta | Development | Web | Recurring | External | l
|  |  | Gamma | Finance | Marketing banners | Subscription |  | m
|  |  | Delta | Administration | Webpage |  |  | yard
|  |  |  | Acquisition | App dashboard |  |  | kg
|  |  |  | Construction | Office |  |  | m²
[5 empty] | Customs |  |  | m³
[5 empty] | Labor |  |  | week
month
year
Manage your project with Plaky
Help
Main table

## Help
Project Budgeting Template | Help: How to use and customize this template
Manage your project with Plaky
Settings
Main table
In this template you can track your project budget for 1 project or multiple projects at once. You can also customize the template to fit your particular project. However, not all fields can be customized, so read on to find out how to use and customize this template one column at a time.
Notes
The table is customizable. The exact ways you can customize the table are explained in the text below (look for the subheading with the name of the column you wish to customize).
If you want to add more columns/rows in between existing columns/rows, it’s best to add them to the entire sheet rather than to the table, otherwise the formatting will get wonky.
Simply writing something in the column/row adjacent to the last column/row will automatically add a new column/row to the table. The end of the table is marked by a tiny arrow in the bottom right corner of the last cell in the table.
You can have as many columns/rows in the table as you need. Adding a new row to the table will automatically extend the formulas to the new row.
In the case that automatic calculations stop working, it likely means that you have accidentally deleted a formula from that cell. To fix it you can:
- Click “Undo” if the change was recent,
- Copy and paste the formula from a different cell that works, or
- Click on a cell that still has the correct formula, click on the little arrow/square at the bottom right of the cell and drag it to select all the cells in the column (this method copies the same formula to all cells selected in this way).
Project
The “Project” column is used for writing down the name of your project for which you’re tracking the budget. If you plan to track the budget for only one project, you may delete this column by deleting the entire B column in the Excel sheet.
However, it is recommended that you still keep the column because you can easily rename it and use it for other purposes (e.g., You can rename the “Project” column to “Task” and the adjacent “Task” column to “Subtask” to get an additional hierarchy level).
If you do plan on tracking the budget for multiple projects, write the name of the correct project in the “Project” column to mark which project the task you’re tracking belongs to.
This might look chaotic at first glance, but it will be very useful when you filter the table by clicking on the arrow button in the header of each column (you’ll be able to filter the table to show you only the tasks and budgets for the project(s) you choose).
If you go to the “Settings” tab, you’ll see a gray table where you can replace the options that show up in the dropdowns, including the “Project” dropdown. Feel free to delete whatever options are currently in the table and replace them with your own.
You can keep adding options as long as there are gray fields in the columns. If you need more fields, simply add another row somewhere in between the gray rows (it won’t work if you add another field at the very end).
Task
The “Task” column is where you write the name of the task or subtask you’re tracking the budget for. Make sure the name is short and clearly describes what the task/activity is.
Category/Subcategory/Type/inter & Exeter
The following 4 columns are where you can further categorize your tasks so that you can easily find them and filter them later on. Feel free to completely change the names of the columns directly in the table, as well as the options that show up in the dropdown by going to the “Settings” page.
If you need more categorization options you can add another column to the table. When adding columns in between other, existing columns, it’s best that you do this by adding a column to the entire sheet rather than to the table itself, otherwise the formatting will get wonky.
Description
This is where you may write a more detailed description of the task you’re tracking the budget for. If this seems unnecessary, you can change the title of this column to something else and repurpose it.
Estimated materials/resource expenses
This section of the table consists of 4 columns:
- Estimated quantity,
- Unit,
- Estimated price per unit, and
- Estimated cost.
The first 3 columns are where you input the details of what exactly is causing you to spend money for that particular task. This is the “plan” of how many things (items, materials, etc.) you think you will need and how much you believe everything will cost per item.
The last column in this section (Estimated cost) is an automatically calculated column based on the information you input into the first 3 columns (it’s a simple formula that multiplies the estimated quantity by the estimated price per unit). Do not write or delete anything in this column. The fields will update automatically as you update the rest of the information.
The “Unit” is a customizable dropdown (Go to the “Settings” page to add/remove/change the items on the list.
Once it’s filled out, it’s recommended that you don’t change this section of the table until the project ends so that you can have an accurate idea of how well you estimated your project costs.
At the top of the section is a cell that sums all the estimated costs in the table and shows the total.
Feel free to change the name of this section. You may also change the purpose of this section if you want to, but keep in mind that this might invalidate some other sections in the table, such as the cost variance column that calculates difference between the estimated and actual costs and the final section that calculates the totals, so it’s not recommended that you do this.
Actual materials/resource expenses
This section is exactly the same as the Estimated materials/resource section, except that it measures how much materials you actually end up needing and how much they actually cost.
Same as with the previous section, the first 3 columns are where you input information, and the last column is where the table will automatically calculate the total. Please don’t write or delete anything from the “Actual cost” column.
For more information, read the section about the “Estimated materials/resource expenses” above. The two are identical, just used for different purposes.
Cost variance
The cost variance is an automatic column that calculates the difference between the final estimated cost and the final actual cost for the materials and shows whether you’ve spent more, less, or exactly what you expected to spend.
The numbers where you exceeded your estimated budget will be colored red.
Contingency budget
This section contains 2 columns:
- The percentage and
- The total contingency budget.
The percent is what you will manually input into the column.
The Total is automatically calculated based on the percentage you input.
The percentage is calculated from the total “Allocated Budget Per Task” in the final section of the table.
In other words, once you allocate the money to a task, write down the percentage of that allocated money that you wish to go toward your contingency budget, and the table will automatically calculate how much money that is exactly.
Contingency expenses
This is where you write down any unexpected expenses you encounter for that particular task over the course of the project.
If the cost of your contingency expense exceeds the contingency budget for that task, the number will appear red.
Unfortunately, there is no way to input multiple contingency expenses in a well-structured manner, so the only option if you have multiple contingency expenses for a task is to write them all together and sum their total cost.
Budget
The final section of this table contains 3 columns:
- Allocated budget per task,
- Estimated budget per task, and
- The total actual cost per task.
The “Allocated budget per task” column is where you write how much money you assigned to the task (a portion of this budget will be set aside for contingency purposes)
The “Estimated budget per task” column is where you write how much you expect the entire task to cost.
The “Actual cost per task” is an automatic column that shows the total money spent on a particular task. The formula in this column calculates the actual cost spent on your materials/resources, and the money spent on contingencies. If the total actual cost per task exceeds the allocated budget per task, the number will show red.
We hope this template will be useful!

## Disclaimer
Project Budgeting Template | Disclaimer
Manage your project with Plaky
Settings
Main table
Help
This template is for reference only.
Plaky aims to provide the most accurate and up-to-date information at all times. Plaky makes no warranties or representations of any kind, expressed or implied, about the accuracy, completeness, and reliability of the information and formulas provided in this template. Plaky shall not be liable for any indirect, incidental, special, consequential, or exemplary damages, or any loss of profits or revenues caused directly or indirectly by the use of this template. Plaky shall not be liable for any loss of data, goodwill, use, or any other intangible losses arising out of your access to, use, or inability to use this template. Use this template at your own risk.