## Project Budget
Resource planning & budgeting template
Project manager: |  |  | Alyssa S.
Total project budget: |  |  | 2000000
Estim. project budget: |  |  | 1800000
Actual total costs: |  |  | 27580
Total spent
[8 empty] | 27980 |  |  |  | 26330 |  |  |  |  | 0 |  | 1250 |  | 27580
[8 empty] | Estm. materials/resource expenses |  |  |  | Actual materials/resource expenses |  |  |  |  | Contingency budget (from allocated) |  | Contingency expenses |  | Budget
Project | Task | Resource | Category | Subcategory | Type | Inter/Exter | Description | Estm. Quantity | Unit | Estm. price per unit | Estm. cost | Actual quantity | Unit | Actual price per unit | Actual cost | Cost variance | % | Total | Description | Cost | Allocated budget/task | Estm. budget per task | Actual budget per task
Alpha | New drawing tablets |  | Design | Office | One-time | Internal | Added new members, need new equipment | 3 | pcs | 650 | 1950 | 2 | pcs | 650 | 1300 | 650 | 10% |  | 1 new GPU + installation fees (GPU broke) | 1250 | 3000 | 1950 | 2550
Beta | Customs fee |  | Acquisition | Customs | One-time | External | Customs fee for transport of X parts | 1 | pcs | 30 | 30 | 1 | pcs | 30 | 30 | 0 | 5% |  |  |  | 800 | 600 | 30
Beta | Construction workers' wage |  | Construction | Labor | Recurring | External | Weekly wages for construction workers | 52 | week | 500 | 26000 | 50 | pcs | 500 | 25000 | 1000 | 15% |  |  |  | 30000 | 26000 | 25000
Gamma

## Settings
Settings
NOTE: | The table below is the basis for all the dropdown lists in the main table. All the data in the table below is purely sample data. You're invited to delete/change/add items as you see fit. E.g., if you want your "Category" dropdown to show different options than it does currently, simply delete everything in the "Category" column below and write your own, custom options. Whatever you write in these columns will appear in the dropdown lists in the corresponding column in the main table. Once you're ready to start using this template, it's recommended that you delete everything in the table below and start from scratch so that you can customize the options to fit your specific project(s). Likewise, you may change the column titles in the main table if the current ones don't fit your project; just make sure not to change the purpose of the columns that are included in table formulas (e.g., the "allocated budget for materials" column can have a different name, but it must be used for that exact purpose; otherwise, the cost variance calculation and the budget calculations at the end of the table won't make sense). For more in-depth instructions on how to customize this template, go to the Help tab in the bottom left corner or use the button at the top right of the page.
|  |  | Project | Category | Subcategory | Type | Inter/Exter | Unit
|  |  | Alpha | Design | Product | One-time | Internal | pcs
|  |  | Beta | Development | Web | Recurring | External | l
|  |  | Gamma | Finance | Marketing banners | Subscription |  | m
|  |  | Delta | Administration | Webpage |  |  | yard
|  |  |  | Acquisition | App dashboard |  |  | kg
|  |  |  | Construction | Office |  |  | m²
[5 empty] | Customs |  |  | m³
[5 empty] | Labor |  |  | week
month
year

## Disclaimer
Disclaimer
This template is for reference only.
Plaky aims to provide the most accurate and up-to-date information at all times. Plaky makes no warranties or representations of any kind, expressed or implied, about the accuracy, completeness, and reliability of the information and formulas provided in this template. Plaky shall not be liable for any indirect, incidental, special, consequential, or exemplary damages, or any loss of profits or revenues caused directly or indirectly by the use of this template. Plaky shall not be liable for any loss of data, goodwill, use, or any other intangible losses arising out of your access to, use, or inability to use this template. Use this template at your own risk.