## Dashboard
Project Management Dashboard Template |  |  |  |  | Jan 3, 2024 — Oct 16, 2024
Start date: | 2024-02-26 |  | Project manager: |  | Peter Maxwell | [8 empty] | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16
Task | Subtask | Priority | Department | Assignee | Manager | Status | Start date | Dur. | Due date | Days left | Progress | Budget | Actual cost | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Task1 | Subtask1 | Low | Development | Jasmine C. | Kevin J. | In Review | 2024-01-11 | 3 | 2024-01-15 | -41 | 100% | 1000 | 999
| Subtask2 | Medium | Marketing | Tom D. | Prudence P. | In Progress | 2024-01-08 | 40 | 2024-03-01 | -7 | 95% | 1000 | 1000 | bar: 2024-03-20
| Subtask3 | Critical! | Marketing | Jenna A. | Prudence P. | On Hold | 2024-02-27 | 22 | 2024-03-27 | 13 | 20% | 1000 | 1001
| Subtask4 | High | Security | Samantha F. | Sasha H. | Overdue | 2024-02-14 | 7 | 2024-02-22 | -13 | 5% | 5000 | 4500
Task1 Total | [10 empty] | 55% | 8000 | 7500
Task2 | Subtask1.1 | Medium | Design | George H. | Jason B. | On Hold | 2024-02-02 | 14 | 2024-02-21 | -14 | 15% | 23000 | 12000
| Subtask2.1 | High | Content | David E. | Helen C. | Complete | 2024-02-20 | 25 | 2024-03-25 | - | 100% | 43000 | 40000
| Subtask3.1 | Medium | Development | Davina B. | Kevin J. | Overdue | 2024-01-28 | 20 | 2024-02-23 | -12 | 50% | 6000 | 6600
| Subtask4.1 | Low | Development | Davina B. | Kevin J. | In Progress | 2024-01-11 | 40 | 2024-03-06 | -4 | 30% | 16000 | 16200
Task2 Total | [10 empty] | 48.75% | 88000 | 74800
Task3 | Subtask1.2 | Low | Design | George H. | Jason B. | Overdue | 2024-01-05 | 37 | 2024-02-26 | -11 | 70% | 2000 | 2000
| Subtask2.2 | Medium | Development | Jasmine C. | Kevin J. | Complete | 2024-01-10 | 20 | 2024-02-06 | - | 100% | 22000 | 23500
| Subtask3.2 | Critical! | Content | David E. | Helen C. | Complete | 2024-01-11 | 14 | 2024-01-30 | - | 100% | 1800 | 1500
| Subtask4.2 | High | Content | David E. | Helen C. | In Progress | 2024-02-12 | 30 | 2024-03-22 | 10 | 30% | 19000 | 21300
Task3 Total | [10 empty] | 75% | 44800 | 48300
Task4 | Subtask1.3 | Low | Security | Samantha F. | Sasha H. | On Hold | 2024-10-16 | (blank) |  | - |  | 9000 | 0
| Subtask2.3 | Medium | Security | Alexander G. | Sasha H. | Complete | 2024-01-03 | 28 | 2024-02-09 | - | 100% | 34000 | 33700
| Subtask3.3 | Medium | Marketing | Tom D. | Prudence P. | In Review | 2024-01-06 | 12 | 2024-01-23 | -35 | 100% | 11500 | 11100
| Subtask4.3 | Medium | Development | Tom D. | Kevin J. | In Progress | 2024-01-28 | 100 | 2024-06-14 | 70 | 10% | 3800 | 800
Task4 Total | [10 empty] | 70% | 58300 | 45600
Task5 | Subtask1.4 | Medium | Development | Davina B. | Kevin J. | In Progress | 2024-01-07 | 120 | 2024-06-21 | 75 | 25% | 4900 | 2000
| Subtask2.4 | Critical! | Content | David E. | Helen C. | On Hold | 2024-01-08 | 35 | 2024-02-23 | -12 | 80% | 5000 | 600
| Subtask3.4 | Medium | Marketing | Tom D. | Prudence P. | Overdue | 2024-01-23 | 20 | 2024-02-19 | -16 | 5% | 23000 | 20000
| Subtask4.4 | High | Security | Alexander G. | Sasha H. | In Review | 2024-01-18 | 40 | 2024-03-13 | 3 | 100% | 43000 | 36000
Task5 Total | [10 empty] | 52.5% | 75900 | 58600
Task6 | Subtask1.5 | Low | Marketing | Jenna A. | Prudence P. | Overdue | 2024-01-21 | 37 | 2024-03-12 | 2 | 50% | 6000 | 9000
| Subtask2.5 | Low | Design | George H. | Jason B. | Complete | 2024-01-12 | 20 | 2024-02-08 | - | 100% | 16000 | 16300
| Subtask3.5 | High | Security | Alexander G. | Sasha H. | Not started | 2024-04-16 | (blank) |  | - |  | 2000 | 0
| Subtask4.5 | Medium | Design | George H. | Jason B. | In Progress | 2024-01-03 | 20 | 2024-01-30 | -30 | 70% | 22000 | 18600
Task6 Total | [10 empty] | 73.33% | 46000 | 43900
Task7 | Subtask1.6 | Low | Content | David E. | Helen C. | On Hold | 2024-02-06 | (blank) |  | - |  | 13600 | 0
| Subtask2.6 | Medium | Development | Peter I. | Kevin J. | Complete | 2024-01-28 | 37 | 2024-03-19 | - | 100% | 14500 | 15700
| Subtask3.6 | Critical! | Development | Jenna A. | Kevin J. | Blocked | 2024-02-27 | 20 | 2024-03-25 | 11 | 30% | 20000 | 4000
| Subtask4.6 | Low | Marketing | Tom D. | Prudence P. | Complete | 2024-01-14 | 14 | 2024-02-01 | - | 100% | 10000 | 12000
Task7 Total | [10 empty] | 76.67% | 58100 | 31700
Grand Total | [10 empty] | 63.4% | 379100 | 310400
82%
Go to Project
Manage your project in Plaky
25%
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Settings
Help

## Project Table
Project Management Template With Dashboard
Project manager | Peter Maxwell | Client |  | Project summary
Project start date | 2024-02-26 | Sponsor |  | The goal of this project is to…
Project end date |  | Total budget
Task | Subtask | Priority | Description | Department | Assignee | Manager | Status | Progress | Start date | Duration | Due date | Days left | Budget | Actual cost | Notes
Task | Subtask3.6 | Critical! |  | Development | Jenna A. | Kevin J. | Blocked | 30% | 2024-02-27 | 20 | 2024-03-25 | -261 | 20000 | 4000
Task | Subtask2.1 | High |  | Content | David E. | Helen C. | Complete | 100% | 2024-02-20 | 25 | 2024-03-25 | -261 | 43000 | 40000
Task | Subtask2.2 | Medium |  | Development | Jasmine C. | Kevin J. | Complete | 100% | 2024-01-10 | 20 | 2024-02-06 | -295 | 22000 | 23500
Task | Subtask3.2 | Critical! |  | Content | David E. | Helen C. | Complete | 100% | 2024-01-11 | 14 | 2024-01-30 | -300 | 1800 | 1500
Task | Subtask2.3 | Medium |  | Security | Alexander G. | Sasha H. | Complete | 100% | 2024-01-03 | 28 | 2024-02-09 | -292 | 34000 | 33700
Task | Subtask2.5 | Low |  | Design | George H. | Jason B. | Complete | 100% | 2024-01-12 | 20 | 2024-02-08 | -293 | 16000 | 16300
Task | Subtask2.6 | Medium |  | Development | Peter I. | Kevin J. | Complete | 100% | 2024-01-28 | 37 | 2024-03-19 | -265 | 14500 | 15700
Task | Subtask4.6 | Low |  | Marketing | Tom D. | Prudence P. | Complete | 100% | 2024-01-14 | 14 | 2024-02-01 | -298 | 10000 | 12000
Task | Subtask4.1 | Low |  | Development | Davina B. | Kevin J. | In Progress | 30% | 2024-01-11 | 40 | 2024-03-06 | -274 | 16000 | 16200
Task | Subtask4.2 | High |  | Content | David E. | Helen C. | In Progress | 30% | 2024-02-12 | 30 | 2024-03-22 | -262 | 19000 | 21300
Task | Subtask4.3 | Medium |  | Development | Tom D. | Kevin J. | In Progress | 10% | 2024-01-28 | 100 | 2024-06-14 | -202 | 3800 | 800
Task5 | Subtask1.4 | Medium |  | Development | Davina B. | Kevin J. | In Progress | 25% | 2024-01-07 | 120 | 2024-06-21 | -197 | 4900 | 2000
Task5 | Subtask4.5 | Medium |  | Design | George H. | Jason B. | In Progress | 70% | 2024-01-03 | 20 | 2024-01-30 | -300 | 22000 | 18600
Task5 | Subtask2 | Medium |  | Marketing | Tom D. | Prudence P. | In Progress | 95% | 2024-01-08 | 40 | 2024-03-01 | -277 | 1000 | 1000
Task1 | Subtask1 | Low |  | Development | Jasmine C. | Kevin J. | In Review | 100% | 2024-01-11 | 3 | 2024-01-15 | -311 | 1000 | 999
Task1 | Subtask3.3 | Medium |  | Marketing | Tom D. | Prudence P. | In Review | 100% | 2024-01-06 | 12 | 2024-01-23 | -305 | 11500 | 11100
Task1 | Subtask4.4 | High |  | Security | Alexander G. | Sasha H. | In Review | 100% | 2024-01-18 | 40 | 2024-03-13 | -269 | 43000 | 36000
Task1 | Subtask3.5 | High |  | Security | Alexander G. | Sasha H. | Not started |  | 2024-04-16 |  |  | - | 2000 | 0
Task1 | Subtask3 | Critical! |  | Marketing | Jenna A. | Prudence P. | On Hold | 20% | 2024-02-27 | 22 | 2024-03-27 | -259 | 1000 | 1001
Task2 | Subtask1.1 | Medium |  | Design | George H. | Jason B. | On Hold | 15% | 2024-02-02 | 14 | 2024-02-21 | -284 | 23000 | 12000
Task4 | Subtask1.3 | Low |  | Security | Samantha F. | Sasha H. | On Hold |  | 2024-10-16 |  |  | - | 9000 | 0
Task4 | Subtask2.4 | Critical! |  | Content | David E. | Helen C. | On Hold | 80% | 2024-01-08 | 35 | 2024-02-23 | -282 | 5000 | 600
Task7 | Subtask1.6 | Low |  | Content | David E. | Helen C. | On Hold |  | 2024-02-06 |  |  | - | 13600 | 0
Task7 | Subtask4 | High |  | Security | Samantha F. | Sasha H. | Overdue | 5% | 2024-02-14 | 7 | 2024-02-22 | -283 | 5000 | 4500
Task7 | Subtask3.1 | Medium |  | Development | Davina B. | Kevin J. | Overdue | 50% | 2024-01-28 | 20 | 2024-02-23 | -282 | 6000 | 6600
Task3 | Subtask1.2 | Low |  | Design | George H. | Jason B. | Overdue | 70% | 2024-01-05 | 37 | 2024-02-26 | -281 | 2000 | 2000
Task3 | Subtask3.4 | Medium |  | Marketing | Tom D. | Prudence P. | Overdue | 5% | 2024-01-23 | 23 | 2024-02-22 | -283 | 23000 | 20000
Task6 | Subtask1.5 | Low |  | Marketing | Jenna A. | Prudence P. | Overdue | 50% | 2024-01-21 | 37 | 2024-03-12 | -270 | 6000 | 9000
Formulas:
Due date = IF(AND([Start date]<>"",[Duration]<>""),WORKDAY.INTL([Start date]-1,[Duration],1,Settings!$G4:G52),"")
Days left = IF(OR('Project Table'!$[Progress]="Complete",ProjectTable[[#This Row],[Due date]]=""),"-",NETWORKDAYS.INTL(TODAY(),'Project Table'!$[Due date],1,Settings!$G4:G43))
Dashboard
Manage your project in Plaky
Settings
Help
Note on D6: To change the values in the dropdown list, go to the next sheet and simply replace a value with a custom one in the "Priority dropdown" column. Example: You wish to replace the value "Medium" in the dropdown list to "Unknown". Step1: Click on "Sheet2" at the bottom left of the screen. Step2: In the "Priority dropdown" column, locate the cell that says "Medium". Step3: Delete "Medium" and replace it with "Unknown" (or any other value of your choosing). You can use the same method to replace the values in the dropdown list of the "Status" column.
Note on J6: You can choose the percentage via the dropdown list, or you can type in a custom number. Note: The bar will not automatically change to "100%" if the status is changed to "Complete".

## Settings
Settings
[5 empty] | Holidays | Today's date: | 2025-03-26
Priority dropdown | Status dropdown | Department | Assignee | Manager | 2024-12-25 | Show "i" notification | 4 | days before the deadline
High | In Progress | Development | Jenna A. | Kevin J. | 2024-07-04
Medium | Complete | Marketing | Davina B. | Helen C.
Low | In Review | Security | Jasmine C. | Sasha H.
Critical! | On Hold | Design | Tom D. | Prudence P.
| Blocked | Content | David E. | Jason B.
| Overdue | Project management | Samantha F.
| Not started | HR | Alexander G.
|  | QA | George H.
|  | Finance | Peter I.
Support
Sales
Administration
SEO
PR
Product management
Product 1
Product 2
Product 3
Manage your project in Plaky
Go to Project
Help
Dashboard

## Formulae for the dashboard
Status dropdown |  |  | Actual cost | Budget |  |  | % Duration of project |  |  |  | Remaining % of project
|  | Bar chart | 310400 | 379100 | Scroll bar: | 23 | Task | Subtask | Status | Duration | Number of tasks total | 28 | Today's date: | 45742
In Progress | 6 | Doughnut | 81.88% | 18.12% |  |  | Task1 | Subtask1 | In Review | 3 | Number of "Complete" tasks | 7
Complete | 7 | [6 empty] | Subtask2 | In Progress | 40 | Number of remaining tasks | 21
In Review | 3 | [6 empty] | Subtask3 | On Hold | 22
On Hold | 5 | [6 empty] | Subtask4 | Overdue | 7 | Complete | 25%
Blocked | 1 | [5 empty] | Task2 | Subtask1.1 | On Hold | 14 | Remaining | 75%
Overdue | 5 | [6 empty] | Subtask2.1 | Complete | 25
Not started | 1 | [6 empty] | Subtask3.1 | Overdue | 20
[8 empty] | Subtask4.1 | In Progress | 40
[7 empty] | Task3 | Subtask1.2 | Overdue | 37
Remaining tasks | 7 | [6 empty] | Subtask2.2 | Complete | 20
Total tasks | 28 | [6 empty] | Subtask3.2 | Complete | 14
[8 empty] | Subtask4.2 | In Progress | 30
[7 empty] | Task4 | Subtask1.3 | On Hold | (blank)
[8 empty] | Subtask2.3 | Complete | 28
[8 empty] | Subtask3.3 | In Review | 12
[8 empty] | Subtask4.3 | In Progress | 100
[7 empty] | Task5 | Subtask1.4 | In Progress | 120
[8 empty] | Subtask2.4 | On Hold | 35
[8 empty] | Subtask3.4 | Overdue | 20
[8 empty] | Subtask4.4 | In Review | 40
[7 empty] | Task6 | Subtask1.5 | Overdue | 37
[8 empty] | Subtask2.5 | Complete | 20
[8 empty] | Subtask3.5 | Not started | (blank)
[8 empty] | Subtask4.5 | In Progress | 20
[7 empty] | Task7 | Subtask1.6 | On Hold | (blank)
[8 empty] | Subtask2.6 | Complete | 37
[8 empty] | Subtask3.6 | Blocked | 20
[8 empty] | Subtask4.6 | Complete | 14

## Help
Help: How to use and customize this template
Manage your project in Plaky
Go to Project
Settings
Dashboard
Title bar — Dashboard:
The title bar in the dashboard sheet shows the project title and the duration of the project (the data reflects the earliest start date and the latest end date from the table).
You may change the project title manually. There is no need to change the project start and end dates—these will update automatically as you change the start and end dates in the table, or as you filter the table.
Chart area:
Under the title bar, you’ll find the area showing the main project charts:
- The total completed percentage of the project,
- The status bar reflecting the number of tasks by status (hover over the bar to see what each color represents),
- The total budget spent, and
- The comparison between the planned and actual budget for the entire project.
These charts reflect the information from the table. In case they fail to present the accurate information, go to Data > Refresh.
Title area2:
Under the chart area, you’ll find a field showing your project start date and project manager. These fields reflect the same fields from the table on the “Project table” tab.
Unlike the start and end dates of the project at the very top of the template that change as you update the project table or filter the data, this project start date will not change unless you change the start data in the “Project table” tab of the template.
To the right of this field, you’ll also find a “Go to Project” button that will lead you directly to the just mentioned “Project table” tab.
Left sidebar:
The slicers enable you to easily filter through the information in the table. You can have multiple filters applied to your data at any one time.
The table can also be filtered using the arrow buttons at the top of each column. If you’d like to add more slicers to the table, go to:
“Insert” tab at the top of the page > Slicer
And then choose which slicers you’d like to insert from the options you’re offered.
Main table:
The main table is a pivot table that reflects all the same data that exists in your “Project table” where you actually track your project. In case the table doesn’t show correct data, go to Data > Refresh.
You can filter the information in the table using the arrow buttons at the top of each column or using slicers. The filtered data will be reflected in the charts above, in the dates at the top of the page, and in the Gantt chart.
Gantt chart:
The Gantt chart shows a visual representation of the start and end dates for your project tasks and their progress. The chart shows 30 days at a time. To see more days, move the scroll bar above the Gantt chart.
The weekends and holidays in the chart are marked with cross-hatching, and today’s date is marked with a blue color and a dark vertical line across the entirety of the chart.
The current Gantt chart is able to show up to 500 days. If you want to change the number of days shown in the Gantt chart, right click on the scroll bar, select “Format Control” and change the “Maximum value” to any number you want.
E.g., if your project is expected to last 2 years, you can increase the maximum value to around 750+. This will account for 365 days x2 with some wiggle room. This number can always be changed.
Title bar — Project table
The title bar in the Project table shows the project title that you can update manually, and the “Go to Dashboard” button that will instantly lead you to the tab with the dashboard.
Project info table:
Under the title chart, you’ll find a table for writing down the start and end dates, name of the project manager, client, and sponsor, as well as the total project budget, and a short project summary.
The name of the project manager and the project start date you write in this table will be reflected in the project dashboard, above the main table.
Main table:
This is the main table, meant to be used for tracking the actual project.
Tasks:
In the tasks field, you can write down the names of your tasks. The task name will replicate multiple times, as long as you keep adding subtasks to it —this is not an error. Because of this, you’ll be able to effectively filter the tasks using the arrow button at the top of the column.
The column next to the “Task” column gives you a quick preview of the tasks that have been completed (will display a checkmark), the tasks that are overdue (will display an X), or tasks whose deadline is 3 days or fewer away (will display a yellow “i” sign). This column is optional, and you may delete it if you think it’s unnecessary.
Subtasks:
In the subtasks column, you can break down each of your tasks into smaller chunks. Be sure to give them a short and recognizable name.
Priority:
The priority column is where you set your subtask’s priority (low, medium, high, or critical) from the dropdown list.
To add or remove priority labels from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Priority dropdown” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 10 to get additional gray rows.
Description:
This is where you add additional information and details about each subtask.
Department:
The department column is where you indicate which team is responsible for a particular task. There are options available in the dropdown list.
To add or remove department options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Department” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 50 to get additional gray rows.
Assignee:
The Assignee column is where you indicate which person is responsible for a particular task. There are options available in the dropdown list.
To add or remove assignee options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Assignee” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 202 to get additional gray rows.
Manager:
The Manager column is where you indicate which person is responsible for the team/assignee for a particular task. There are options available in the dropdown list.
To add or remove manager options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Manager” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 52 to get additional gray rows.
Status:
In the status column, you’ll be able to choose your subtask’s status from a dropdown list. There are currently 7 different types of statuses available in the dropdown list.
To add or remove status options from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Status dropdown” column. You may add new labels as long as there are gray fields left in the column. If you need more labels, you’ll have to insert a new row between rows 3 and 15 to get additional gray rows.
Progress:
The progress column is a visual representation of each subtask’s progress. It does not pull information from any source and must be updated manually. You can choose an option from the dropdown list, or type in a custom percentage.
NOTE: If you type in a custom percentage that doesn’t exist in the dropdown list, the cell will have a small triangle at the top left corner and might indicate that there is an error in the cell. You may ignore this warning as this is a manually updated column and doesn’t affect any of the calculations.
Start date + Duration + End date + Days left
The “Start date” column is where you manually write down the date you expect your subtask to start.
The “Duration” column is where you write down the number of work days you expect your subtask to take (the calculation will exclude weekends and any designated holidays). Once you input the expected duration, the “End date” will automatically show up.
To add or remove holidays from the dropdown list, go to the “Settings” tab at the bottom left of the screen and add/remove/change options in the “Holidays” column. You may add new holidays as long as there are gray fields left in the column. If you need to add more holidays, you’ll have to insert a new row between rows 2 and 41 to get additional gray rows.
Once you have your end date, the “Days left” column will automatically calculate how many days you have left until the deadline, or if your deadline has passed, how many days you are behind schedule.
Budget:
The “Budget” and “Actual cost” columns are where you can manually input your subtask budget and the actual money funds spent on performing that task. The actual cost that exceeds the budget set out for that task will show up in red.
Important!
Please do NOT change or remove anything in the “Formulae for the dashboard” tab at the bottom left of the screen. If you do, the dashboard might not work properly anymore.

## Disclaimer
Disclaimer
Dashboard
Settings
Help
Manage your project in Plaky
This template is for reference only.
Plaky aims to provide the most accurate and up-to-date information at all times. Plaky makes no warranties or representations of any kind, expressed or implied, about the accuracy, completeness, and reliability of the information and formulas provided in this template. Plaky shall not be liable for any indirect, incidental, special, consequential, or exemplary damages, or any loss of profits or revenues caused directly or indirectly by the use of this template. Plaky shall not be liable for any loss of data, goodwill, use, or any other intangible losses arising out of your access to, use, or inability to use this template. Use this template at your own risk.
Go to Project