## Issue tracker
|  | Issue Tracker Template |  |  |  |  | Department: | Development | Project Owner: | Maria A.
|  | Status/Priority | High | Medium | Low | Total |  | Overdue
|  | To do | 1 | 0 | 0 | 1 |  | 5
|  | In progress | 2 | 0 | 1 | 3
|  | Done | 0 | 1 | 0 | 1
|  | In review | 1 | 0 | 0 | 1
|  | At risk | 0 | 0 | 0 | 0
|  | Blocked | 0 | 0 | 0 | 0 |  | High priority
|  | Postponed | 0 | 1 | 0 | 1 |  | 4
|  | Discarded | 0 | 0 | 1 | 1
|  | Total | 4 | 2 | 2 | 8
Bug ID | Status | Title/Summary | Severity | Priority | Issue type | Classification | Expected result | Actual result | Step-by-step | Environment | Links | Frequency | Reporter | Assignee | Reported on | Due date | Days left | Date closed | Time logged | Notes/Comments | Resolution
| To do |  | Medium | High | New feature | Security | [5 empty] | Always | Anna A. | Brian B. | 2024-03-02 | 2024-03-15 | - | 2024-03-13
| Done |  | Minor | Medium | Bug | Crash | [5 empty] | Once | Carl C. | Devon D. |  |  | -
| In progress |  | Major | Low | Suggestion | UI/Usability | [5 empty] | Sometimes | Farrah F. | George G. |  | 2024-03-25 | -591
| In review |  | Critical | High |  | Performance | [5 empty] | Rarely | Hannah H. | Evelyn E. |  | 2024-03-15 | -597
| Postponed |  |  | Medium |  | Syntax | [9 empty] | 2024-03-18 | -596
| Discarded |  |  | Low | [11 empty] | 2024-03-14 | -598
| In progress |  |  | High | [11 empty] | 2024-03-12 | -600
| In progress |  |  | High | [12 empty] | -
-
-
-
-
-
-
-
-
-
-
Manage your project with Plaky
Settings

## Settings
Settings
Today's date: | 2026-07-01
| Status | Severity | Priority | Issue type | Classification | Frequency | Reporter | Assignee | Department | Project Owner | Holidays
| To do | Minor | High | New feature | Security | Always | Anna A. | Anna A. | Sales | Maria A. | 2024-12-25
| In progress | Medium | Medium | Suggestion | Performance | Sometimes | Brian B. | Brian B. | Development | Gabriel B. | 2024-07-04
| In review | Major | Low | Bug | Crash | Rarely | Carl C. | Carl C. | Finance | Andrew C.
| Done | Critical |  |  | UI/Usability | Once | Devon D. | Devon D.
| Discarded |  |  |  | Syntax |  | Evelyn E. | Evelyn E.
| Postponed | [5 empty] | Farrah F. | Farrah F.
| Blocked | [5 empty] | George G. | George G.
| At risk | [5 empty] | Hannah H. | Hannah H.
Manage your project with Plaky
Main table

## Disclaimer
Disclaimer
Manage your project with Plaky
Settings
Main table
This template is for reference only.
Plaky aims to provide the most accurate and up-to-date information at all times. Plaky makes no warranties or representations of any kind, expressed or implied, about the accuracy, completeness, and reliability of the information and formulas provided in this template. Plaky shall not be liable for any indirect, incidental, special, consequential, or exemplary damages, or any loss of profits or revenues caused directly or indirectly by the use of this template. Plaky shall not be liable for any loss of data, goodwill, use, or any other intangible losses arising out of your access to, use, or inability to use this template. Use this template at your own risk.