## Sheet1
Project Timeline Template | [10 empty] | Project manager: | Andrew S | Project start: | 2024-01-01
Planned timeline | [7 empty] | Actual timeline
Task | Planned start date | Planned work days | Planned end date | Planned Budget | Column2 | Column3 | Column4 | Task2 | Actual start date | Actual work days | Actual end date | Actual cost | Timeline chart start date | Total No. of days | Days completed | % Progress
Website design | 2024-01-01 | 55 | 2024-03-18 | 1000 |  |  |  | Website design | 2024-01-01 | 50 | 2024-03-11 | 800 | 2024-01-01 | 70 | 56 | 80%
On-page SEO | 2024-02-05 | 40 | 2024-04-01 | 1200 |  |  |  | On-page SEO | 2024-02-05 | 37 | 2024-03-27 | 1200 | 2024-02-05 | 51 | 25.5 | 50%
New landing page | 2024-03-12 | 30 | 2024-04-23 | 700 |  |  |  | New landing page | 2024-03-12 | 30 | 2024-04-23 | 850 | 2024-03-12 | 42 | 42 | 100%
Task4 | 2024-04-15 | 45 | 2024-06-17 | 900 |  |  |  | Task4 | 2024-04-15 | 40 | 2024-06-10 | 800 | 2024-04-15 | 56 | 22.4 | 40%
Task5 | 2024-05-17 | 70 | 2024-08-26 | 300 |  |  |  | Task5 | 2024-05-17 | 50 | 2024-07-29 | 500 | 2024-05-17 | 73 | 40.15 | 55%
Task6 | 2024-06-23 | 90 | 2024-10-28 | 2000 |  |  |  | Task6 | 2024-06-23 | 105 | 2024-11-18 | 2300 | 2024-06-23 | 148 | 29.6 | 20%
Task7 | 2024-07-28 | 55 | 2024-10-11 | 1400 |  |  |  | Task7 | 2024-07-28 | 60 | 2024-10-18 | 1200 | 2024-07-28 | 82 | 27.06 | 33%
Task8 | 2024-08-04 | 30 | 2024-09-13 | 500 |  |  |  | Task8 | 2024-08-04 | 30 | 2024-09-13 | 450 | 2024-08-04 | 40 | 11.2 | 28%
Task9 | 2024-09-08 | 25 | 2024-10-11 | 700 |  |  |  | Task9 | 2024-09-08 | 20 | 2024-10-04 | 720 | 2024-09-08 | 26 | 20.8 | 80%
Task10 | 2024-10-13 | 60 | 2025-01-06 | 1300 |  |  |  | Task10 | 2024-10-13 | 50 | 2024-12-20 | 1000 | 2024-10-13 | 68 | 68 | 100%
Task11 | 2024-11-17 | 50 | 2025-01-27 | 1000 |  |  |  | Task11 | 2024-11-17 | 45 | 2025-01-20 | 1100 | 2024-11-17 | 64 | 64 | 100%
Task12 | 2024-12-20 | 30 | 2025-02-03 | 2200 |  |  |  | Task12 | 2024-12-20 | 50 | 2025-03-03 | 2000 | 2024-12-20 | 73 | 43.8 | 60%
Select timeline: | Actual timeline
Formulas:
Planned end date = IF([Planned start date]="","",WORKDAY(Sheet1!E5,Sheet1!F5,Settings!$B4:B29))
Actual end date = IF([Planned start date]="","",WORKDAY(Sheet1!M5,Sheet1!N5,Settings!$B4:B29))
Timeline chart start date = IF(Sheet1!$E19="Planned timeline",[Planned start date],[Actual start date])
Manage your project with Plaky
Note on D4: Once you fille out these gray columns with your original project plan timeline, these dates should not change until the end of your project
Note on L4: After you've filled out your planned timeline data, please continue using only the white colums with the dark border around them to update your project timeline information.
Note on Q4: Do NOT write anything in these gray columns! They are filled with formulae from which the timeline draws information. These gray columns will automatically update once you update your Actual timeline data

## Settings
Settings
Holidays | Chart title: | Project manager | Andrew S
2024-12-25 | Actual timeline | Start date | 2024-01-01
2024-07-04
Manage your project with Plaky

## Help
Help: How to use and customize this template
Manage your project with Plaky
Title bar:
The title bar contains the project title, project start date, and the name of the project manager. You can change these directly in the title bar, or you can go to the “Settings” tab in the bottom left of the screen and change this information in the “Project information” table.
Doing it like this will ensure that you never accidentally change or delete the project information while working on the main project timeline sheet.
Main table:
The main project timeline table has 3 important sections:
- Planned timeline,
- Actual timeline, and
- Automatically calculated data.
Planned timeline:
The first 5 columns in the main table comprise the Planned timeline section. This is the section you fill out at the beginning of the project and (ideally) don’t touch from that moment onwards. This will be your baseline for measuring your actual progress in terms of time and budget.
Actual timeline:
The Actual timeline is what comes next. This part is colored white and outlined in black. This is the part that you will be changing and editing throughout the project to reflect the actual time you’ve spent on tasks and the actual amount of money you’ve spent, so that you can compare it to your plans/estimates.
In the “Actual cost” column of this section, the numbers that exceed the planned budget will be colored red.
Automatically calculated data:
The next 3 columns that are colored gray (“Timeline chart start date”, “Total No. of days”, and “Days completed”) are columns you shouldn’t write in.
These columns contain formulae that calculate this data automatically based on the information in the “Planned timeline” and “Actual timeline” sections, as well as the “% Progress” column at the end of the table. This is also where the project timeline below pulls its information from.
NOTE: The current calculations exclude weekends and designated holidays. To remove certain holidays from the equation, or add new ones, go to the “Project information” tab in the bottom left corner and add/remove holidays in the column titled “Holidays”.
% Progress column:
The Progress column is where you manually write your project’s progress. The “Days completed” section will then automatically show the number of days you’ve completed based on the percentage you typed in. This number of days completed will then immediately reflect in the timeline below.
Important!
The “Planned timeline” section is the section you fill out at the beginning of the project. This section should not change until the end of the project.
The only sections you should edit throughout the project are the “Actual timeline” section, and the “% Progress” column. These sections are colored white and outlined in black.
Timeline:
The timeline chart is a reflection of the information shown in the table. You shouldn’t change any information directly in the timeline. The information will automatically update as you update the table above.
Above the timeline chart, you’ll find a dropdown list where you can toggle between the planned timeline view (that reflects the “Planned timeline” section of the table) and the actual timeline view (that reflects the “Actual timeline” section of the table, along with the percentage of work completed)
Budget:
The planned project budget and the actual expenditures are reflected in the “Planned vs Actual budget” bar chart next to the timeline chart.
The chart reflects the information in the table above and makes a visual comparison of the current state of the project. Feel free to change the title of the chart and the chart format as you see fit. The information itself will change automatically as you update the main table above.

## Disclaimer
Disclaimer
Manage your project with Plaky
This template is for reference only.
Plaky aims to provide the most accurate and up-to-date information at all times. Plaky makes no warranties or representations of any kind, expressed or implied, about the accuracy, completeness, and reliability of the information and formulas provided in this template. Plaky shall not be liable for any indirect, incidental, special, consequential, or exemplary damages, or any loss of profits or revenues caused directly or indirectly by the use of this template. Plaky shall not be liable for any loss of data, goodwill, use, or any other intangible losses arising out of your access to, use, or inability to use this template. Use this template at your own risk.